## DSR
DAILY HSE REPORT
Date(s): 21/06/2018 |  |  | Project Name: 24 MW HZL Project, Rampura (MSUT18016)
Issued Gate Pass Status
S.NO | Type Of Gate Pass |  | Issued during Report Period | Cumulative issued in Report Month | Project cumulative issued | Remark during Report Period
1 | Temporary Gate Pass (Worker)
2 | Permanent Gate Pass (Worker)
3 | Temporary Gate Pass (Vehicle)
4 | Permanent Gate Pass (Vehicle)
5 | Visitors Gate Pass
Project Training Status
S.NO | HSE Activities | Conducted by | No of persons attended during Report Period | Training Time period (Hrs/Min./Sec.) | Cumulative Attend in Report Month | Project cumulative Attend (Hrs/Min./Sec.) | Number Of Traning | Training Man Days (Hrs/8) | Remark during Report Period | Links to Pictures taken during Report Period
1 | 5-s Training Program
2 | Confined Space Working Training
3 | Emergency Response training
4 | First Aid Training
5 | Fire Fighting training program
6 | Hot Work Training
7 | Height Work Training
8 | Induction Training
9 | Tool Box Talk |  | 25 | 45 Mins | 25 (45 Mins) | 25 (45 Mins) | 1 | 2.3438
10 | Other Safety training | Mr Nirmal | 15 | 45 Mins | 15 (45 Mins) | 15 (45 Mins) | 1 | 1.4062
11 | Hazards identification & Risk Assessment
12 | Environment Impact Analysis
13 | Human Rights Training
14 | Behaviour Base Safety
15 | Near Miss reporting training
16 | Electrical Safety Training | [7 empty] | heat stroke training
Project HSE Activity Status
S.NO | HSE Activities | Conducted by | Number of observation Observed | Number of activity in report month | Number of Cumulative activity during Project | Remark during Report Period/ (Audit Score %) | Links to Pictures taken during Report Period
Man Power & Working Hours
A | Contractor staff/ Workers/Temp. man power | Hrs. Worked | Man-hours Worked | Total Man Hours during Report Period | Cumulative Man Hours in Report Month | Project Cumulative Man Hours | Average Man power | Monthly Total Manpower | Project Cumulative Manpower
1 | 25 | 8 | 200 | 336 | 3824 | 3824 | 12.8243 | 474 | 474
B | No. of MSPL staff | Hrs. Worked | Man hours Worked
1 | 7 | 8 | 56
C | MSPL Temp. Man Power (FTC) | Hrs. Worked | Man hours Worked
1 | 4 | 8 | 32
D | Security (TPC) | Hrs. Worked | Man-hours Worked
1 | 4 | 12 | 48
Project HSE Statistics
Sl No. | Indicator Name (Unit) | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Project Cumulative
1 | Frequency Rate (FR) = (No. of reportable accident * 1000000)/ Total Man Hours Worked
2 | Severity Rate (SR) = (Man Days Lost due to reportable accident * 1000000)/ Total Man Hours Worked
3 | Incidence Rate (IR) = (Reportable Accident +Non Reportable Accident + First Aid*1000)/Avg. Daily Manpower
4 | Frequency Severity Index (FSI) = SQRT(Frequency Rate* Severity Rate/ 1000)
5 | Near Miss (UA & UC) = No. of Near Miss/ Avg. Man power
6 | SBI = Safe Behaviour/(Safe Behaviour + Unsafe Behaviour)*100
7 | HSE Training Coverage Rate = HSE Training Man Hours * 100 / Report Month Manpower | Jun: 6.3291 | 6.3291
8 | Vehicle Accident Rate = No. of Vehicle Accident * 1000000 / Vehicle mileage (Running KM)
9 | TBT (3Q) Coverage Rate = (No. of person attended) * 100/ Report Month Manpower | Jun: 5.2743 | 5.2743
10 | Occupational Illness Incident Rate = No. of occupational Illness cases x 1000000 / Total Man Hours Worked
Incidents | bar: Jan to Jun
S.NO | Type | Jan: Quantity during Report Period; Feb: Cumulative in Report Month; Mar: Project Cumulative; Apr: Lost time due to Injury in Report Month; May: Project cum. time due to Injury; Jun: Man Days Lost
1 | Near Miss
2 | Fatal Accident
3 | Lost Time Accident (More than 48 Hours)
4 | Lost Time Accident (Lost time upto 48 Hours)
5 | Medical Treatment case(MTC) (lost time upto 8 Hours)
6 | Near Miss Case
7 | Dangrous Occurance/ Incident
8 | First AID Case
9 | Occupational Illness/ Incident case
10 | Property Damage incident
11 | Fire Incident
12 | Environment Incident
13 | Treveling Vehicle Incident
Work Permit Record | bar: Jan to May
S.NO | Type of Permit | Jan: Total Work permit issued during report period; Feb: Cumulative issued in Report Month; Mar: Project cumulative issued; Apr: Type of Permit in report month x Days; May: Type of Permit cumulative x Days
Vehicles Checking | bar: Jan to Oct
Sl No. | Equipment Details | Reg . No | Testing Date | Next Due Date | Vehicle Valid PUC Upto | Reverse horn | Valid License Upto | Insurance Valid Upto | Company/ Agency Name | Driver's name | Remark
Fire fighting equipment | bar: Jan to Sep
Sl No. | Type of Fire Extinguisher | Jan: Serial Number; Feb: Inspection Date; Mar: Next Due Date; Apr: Capacity; May: Location; Jun: OK/Not Ok; Jul: if not ok / Observation
Temprature Monitoring | bar: Jan to Sep
Sl No. | Type of Monitering | Jan: Date Of Monitering; Feb: Time of Monitoring; Mar: Location of monitoring; Apr: Result of Monitering; May: Next Due Date; Jun: Remark
Equipment Checking | bar: Jan to Sep
Sl No. | Name Of Equipment | Jan: Checklist Number; Feb: Equipment Serial Number; Mar: Date Of Checking; Apr: Next Due Date; May: Remark
Sustainability Report
Sl No. | Indicator Name (Unit) | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Quantity Total
Environment Reporting | bar: Jan to Sep
Sl No. | Type of Monitering | Jan: Date of Monitering; Feb: Time of monitering; Mar: Location of monitoring; Apr: Next Due Date; May: Report No.; Jun: Remark
Safe / Unsafe Behaviour
Sl No. | Behaviour Type | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Quantity Total

## Near Miss (UA & UC)
Near Miss (UA & UC)
Date(s): 21/06/2018 |  |  | Project Name: 24 MW HZL Project, Rampura (MSUT18016)
Near Misses
SR. NO. | DATE | Near Miss (UA & UC) | LOCATION | NAME OF CONTRACTOR | NAME OF OBSERVER | ACTION TAKEN | NAME OF CLOSER | DATE OF CLOSE OUT | REMARK | PICTURE LINK

## Work Permit
Work Permit Records
Date(s): 21/06/2018 | [6 empty] | Project Name: 24 MW HZL Project, Rampura (MSUT18016)
Work Permits
S.NO | Permit NO | Type | Issue date | Start Time | Expires Date | Expires Time | Close Time | Location | Work Discription | Contractor | Contractor JOB Incharge | Issuer /Job Incharge MEPC

## First Aid Record
First Aid Record
Date(s): 21/06/2018 |  |  |  |  | Project Name: 24 MW HZL Project, Rampura (MSUT18016)
First Aid
SR. NO. | DATE | DESCRIPTION OF THE INCIDENT | PART OF INJURY | LOST TIME DUE TO INJURY | LOCATION | NAME OF INJURED PERSON | TREATMENT GIVEN | NAME OF FIRST AIDER | REMARKS

## Incident Record
Incident Record
Date(s): 21/06/2018 | [5 empty] | Project Name: 24 MW HZL Project, Rampura (MSUT18016)
Incident
SR. NO. | DATE | INCIDENT TYPE | DESCRIPTION OF THE INCIDENT | PART OF INJURY | LOST TIME DUE TO INJURY | LOCATION | NAME OF INJURED | NAME OF FIRST AIDER | ACTION TAKEN | REPORT NUMBER | REMARKS

## Daily Site Safety observation
Daily Site Safety observation
Date(s): 21/06/2018 | [5 empty] | Project Name: 24 MW HZL Project, Rampura (MSUT18016)
Site Safety Violation
SR. NO. | DATE | NAME AND CONTACT DETAILS OF OBSERVER | LOCATION | SAFETY VIOLATION DESCRIPTION | SEVERITY OF OBSERVATION CLOSER | NAME OF CONTRACTOR | NAME AND CONTACT DETAILS OF JOB RESPONSIBLE | DATE OF OBSERVATION CLOSER | ACTION TAKEN | CORRECTIVE ACTION TAKEN

## Site Safety Violation Record
Site Safety Violation Record
Date(s): 21/06/2018 |  |  |  |  | Project Name: 24 MW HZL Project, Rampura (MSUT18016)
Site Safety Violation
SR. NO. | DATE | NAME AND CONTACT DETAILS OF OBSERVER | LOCATION | SAFETY VIOLATION DESCRIPTION | NAME OF CONTRACTOR | PENALTY ISSUE DETAIL | ACTION TAKEN | CORRECTIVE ACTION TAKEN

## Vehicle Checking Record
Vehicle Checking Record
Date(s): 21/06/2018 |  |  |  | Project Name: 24 MW HZL Project, Rampura (MSUT18016)
Vehicles Checking
SL NO. | EQUIPMENT DETAILS | REG . NO | TESTING DATE | NEXT DUE DATE | VEHICLE VALID PUC UPTO | REVERSE HORN | VALID LICENSE UPTO | INSURANCE VALID UPTO | COMPANY/ AGENCY NAME | DRIVER'S NAME | REMARK

## Fire Fighting Equipment
Fire Fighting Equipment
Date(s): 21/06/2018 |  |  |  | Project Name: 24 MW HZL Project, Rampura (MSUT18016)
Fire Fighting Equipment
SL NO. | Type of Fire Extinguisher | Serial Number | Inspection Date | Next Due Date | Capacity | Location | OK/Not Ok | if not ok / Observation

## Equipment Checking
Equipment Checking
Date(s): 21/06/2018 |  |  |  | Project Name: 24 MW HZL Project, Rampura (MSUT18016)
Equipment Checking
SL NO. | Name Of Equipment | Checklist Number | Equipment Serial Number | Date Of Checking | Next Due Date | Remark

## Training Record
Training Record
Date(s): 21/06/2018 |  |  |  |  | Project Name: 24 MW HZL Project, Rampura (MSUT18016)
Training Record
SL NO. | Date | HSE Activities | Conducted By | No of persons attended | Training Time period | Remark
1 | 21/06/2018 | Tool Box Talk |  | 25 | 45 Mins
2 | 21/06/2018 | Other Safety training | Mr Nirmal | 15 | 45 Mins | heat stroke training

## HSE Activity
HSE Activity
Date(s): 21/06/2018 |  |  |  |  | Project Name: 24 MW HZL Project, Rampura (MSUT18016)
HSE Activity
SL NO. | Date | HSE Activities | Conducted By | Type of activity | Number of observation Observed | Remark